## Consolidated_AN (hidden)
Sr No | Segment | Sub Segment | Action Pointers | Timeline | Current Status
90 | Product | Vol 1 | First Round Sketches | 2025-03-21 | Completed
91 | Product | Vol 1 | AUR Meeting | 2025-03-24 | Completed
92 | Product | Vol 1 | Feedback from Ms Birla | 2025-04-07 | Completed
81 | Product | Vol 0 | SMS Feedback (with Marketing and Sales) | 2025-04-14 | WIP
82 | Product | Vol 0 | -SMS Order Confirmation by Brand - 300 pairs | 2025-04-14 | WIP
83 | Product | Vol 0 | -Fit Test | 2025-04-14 | WIP
119 | Product | Vol 0 | Finalising Contract Manufacturing Agreement | 2025-04-14 | WIP
120 | Product | Vol 0 | Finslaising R&D Agreement | 2025-04-14 | WIP
121 | Product | Vol 0 | Freeze on Vol 0 and Vol 0.5 assortment | 2025-04-14 | WIP
122 | Product | Vol 0 | Fit Test (Internal +External) Reporting | 2025-04-14 | WIP
123 | Product | Vol 0 | Mould decision on sizes/ styles | 2025-04-14 | WIP
124 | Product | Vol 0 | Finalising RRP for Volume 0 | 2025-04-14 | WIP
125 | Product | Vol 0 | Closure on packaging – Box, Dustbag, butter paper, Hang tags | 2025-04-14 | WIP
136 | Product | Vol 0 | Finalising Final Colors,Styles for Vol 0 | 2025-04-14 | WIP
137 | Product | Vol 0 | Discussion on extension to current designs | 2025-04-14 | WIP
127 | Marcom | Vol 0 | Transfer of Goods from Mumbai to HS (EUR 39) | 2025-04-16
130 | Operations |  | Creating Process Flowchart | 2025-04-16 | WIP
131 | Operations |  | Operationalising Param and Zoho | 2025-04-16 | WIP
132 | Operations |  | Creating ERP for Product Placement | 2025-04-16 | WIP
126 | Product | Vol 1 | Transfer of Goods from Mumbai to Amsterdam (EUR 43) | 2025-04-16 | Completed
129 | Product | RTW | RTW : Base level discussion and way forward | 2025-04-16 | WIP
133 | Product | Second Factory | Alternate Factory Identification | 2025-04-16 | WIP
134 | Product | Second Factory | Rechecking R&L samples and checking convergence with Sid M / Sid P / Mikey | 2025-04-16 | WIP
135 | Product | BIS | Discussing and proposing final India route plan through BIS factory | 2025-04-16 | WIP
128 | Trademark | Vol 0 | Transfer AUR TM ownership from Sid M to TACPL | 2025-04-16 | Completed
52 | Marcom | Website Production | Closure on brief from HS | 2025-04-17
8 | Marcom | Brand Foundations | Closure on Brand Name and Logo | 2025-04-19
9 | Marcom | Brand Foundations | Closure on Brand Colours | 2025-04-19
84 | Product | Vol 0 | -Mould Opening Confirmation by brand | 2025-04-20 | Completed
85 | Product | Vol 0 | -Order Placement - Sales Order Vol 0 and 0.5 | 2025-04-20 | WIP
7 | Marcom | Brand Foundations | Closure on Brand Ethos | 2025-04-21
10 | Marcom | Brand Foundations | Closure on Social Handles | 2025-04-22
53 | Marcom | Website Production | Closure on custom versus shopify | 2025-04-22
93 | Product | Vol 1 | Second Round Sketches | 2025-04-22 | Completed
94 | Product | Vol 1 | Presentation_Second Round Skeches | 2025-04-22
44 | Marcom | Media Planning | Closure on Agency in terms of scope | 2025-04-23
138 | Operations | Vol 0 | Finalisation of R&D Agreement | 2025-04-23 | WIP
139 | Operations | Vol 0 | Finalisation of CMA Agreement | 2025-04-23 | WIP
95 | Product | Vol 1 | Feedback from Ms Birla | 2025-04-25
11 | Marcom | Brand Foundations | Closure on Packaging | 2025-04-26
12 | Marcom | Campaign Production | Create Campaign Gannt | 2025-04-26
45 | Marcom | Media Planning | Closure on Agency wrt costs negotiations | 2025-04-26
63 | Marcom | Ms Birla's Role | Align on a brief for HS | 2025-04-26
140 | Operations | Vol 0 | Factory Mould Payment | 2025-04-30
141 | Operations | Vol 0 | Production Order Payment | 2025-04-30
13 | Marcom | Campaign Production | Finalise Assets | 2025-05-01
19 | Marcom | Social Media | Finalise on channel strategy | 2025-05-05
20 | Marcom | Social Media | Finalise on content pillars | 2025-05-05
23 | Marcom | Social Media | Closure on goals | 2025-05-05
24 | Marcom | Social Media | Closure on Talent for various stages | 2025-05-05
25 | Marcom | Social Media | - Tagged not posted | 2025-05-05
26 | Marcom | Social Media | - I'll take N17 and wedding invite | 2025-05-05
27 | Marcom | Social Media | - GRWM Videos | 2025-05-05
28 | Marcom | Social Media | - Wedding coverage | 2025-05-05
29 | Marcom | Social Media | - Always on UGC | 2025-05-05
46 | Marcom | Media Planning | Final brief | 2025-05-05
64 | Marcom | Ms Birla's Role | First cut presentation from HS | 2025-05-05
96 | Product | Vol 1 | First Draft Colors with proposed materials | 2025-05-08
97 | Product | Vol 1 | SH to share swatch package to be developed for remote presentation dispatched from Amsterdam | 2025-05-09
54 | Marcom | Website Production | First cut designs for Ecom | 2025-05-14
65 | Marcom | Ms Birla's Role | Final presentation from HS | 2025-05-14
67 | Marcom | Ms Birla's Role | Approval plan | 2025-05-14
14 | Marcom | Campaign Production | Closure on production house | 2025-05-15
15 | Marcom | Campaign Production | Closure on campaign concept | 2025-05-15
16 | Marcom | Campaign Production | Closure on talent and team | 2025-05-15
17 | Marcom | Campaign Production | Closure on shoot dates | 2025-05-15
31 | Marcom | PR Strategy | Finalise on Media | 2025-05-15
32 | Marcom | PR Strategy | - Tier 1 list | 2025-05-15
33 | Marcom | PR Strategy | - Tier 2 list | 2025-05-15
34 | Marcom | PR Strategy | - Tier 3 list | 2025-05-15
35 | Marcom | PR Strategy | Closure on coverage goals | 2025-05-15
49 | Marcom | Media Planning | Asset requirements outlined | 2025-05-15
98 | Product | Vol 1 | Swathe package received in Mumbai | 2025-05-15
99 | Product | Vol 1 | First Draft Colour & Material Selection - with Ms Birla Feedback | 2025-05-19
21 | Marcom | Social Media | 30/ 60 day calendar | 2025-05-20
30 | Marcom | Social Media | Close on regular reporting format | 2025-05-20
43 | Marcom | PR Strategy | Close on regular reporting format | 2025-05-20
47 | Marcom | Media Planning | First cut media plan with goals (follower count, early sign ups/ conversions) | 2025-05-21
48 | Marcom | Media Planning | Set up accounts, Meta Pixel, Google Analytics, etc | 2025-05-21
66 | Marcom | Ms Birla's Role | Execution plan on assets needed | 2025-05-21
51 | Marcom | Media Planning | Close on regular reporting format | 2025-05-25
100 | Product | Vol 1 | Final Sketch with Colors & Materials | 2025-05-26
22 | Marcom | Social Media | Closure on Approval process | 2025-05-30
78 | Marcom | Analytics | Daily performance monitoring dashboard | 2025-05-30
79 | Marcom | Analytics | Weekly Social Media report | 2025-05-30
80 | Marcom | Analytics | Bi-weekly PR & influencer coverage report | 2025-05-30
142 | Operations | Vol 0 | AURLABS TRADING FZE Incorporation | 2025-05-30
143 | Operations | Vol 0 | AURLABS TRADING Bank Account Incorporation | 2025-05-30
144 | Operations | Vol 0 | Onboarding Ripplr | 2025-05-30
86 | Product | Vol 0 | Bulk SMS handover by Factory - 300 pairs | 2025-05-30 | Cancelled
101 | Product | Vol 1 | Feedback from Ms Birla | 2025-05-30
102 | Product | Vol 1 | Upper Specification | 2025-06-13
18 | Marcom | Campaign Production | Asset creation | 2025-06-15
56 | Marcom | Website Production | Handover of assets from HS | 2025-06-15
87 | Product | Vol 0 | Confirmation Sample | 2025-06-15
88 | Product | Vol 0 | Mould Opening Complete | 2025-06-15
103 | Product | Vol 1 | Color Specification | 2025-06-16
104 | Product | Vol 1 | Tech Pack - SH | 2025-06-16
55 | Marcom | Website Production | First cut designs for teaser websites | 2025-06-30
76 | Marcom | Pop Up | Close on gifting if needed | 2025-06-30
36 | Marcom | PR Strategy | Creation of PR kits for various activations (Press release + camapign assets) | 2025-07-05
37 | Marcom | PR Strategy | - Tagged not posted | 2025-07-05
38 | Marcom | PR Strategy | - I'll take N17 and wedding invite | 2025-07-05
39 | Marcom | PR Strategy | - Campaign Launch | 2025-07-05
40 | Marcom | PR Strategy | - Wedding coverage | 2025-07-05
41 | Marcom | PR Strategy | - November outreach | 2025-07-05
42 | Marcom | PR Strategy | - Dec activation outreach | 2025-07-05
50 | Marcom | Media Planning | CRM planning with emailers needed | 2025-07-05
105 | Product | Vol 1 | Prototype 1 | 2025-07-13
57 | Marcom | Website Production | Final designs for Ecom | 2025-07-15
58 | Marcom | Website Production | Final designs for Teaser | 2025-07-15
106 | Product | Vol 1 | Prototype Feedback | 2025-07-23
107 | Product | Vol 1 | Prototype 2 | 2025-08-07
108 | Product | Vol 1 | Prototype Feedback | 2025-08-12
60 | Marcom | Website Production | Integration with Logistics and payment gateways | 2025-08-15
77 | Marcom | Pop Up | Syncing offline sales to Shopify? | 2025-08-15
89 | Product | Vol 0 | Order Dispatch | 2025-08-15
59 | Marcom | Website Production | Development | 2025-08-30
62 | Marcom | Website Production | Testing | 2025-08-30
69 | Marcom | Loyalty Plan | Work with Bertan and HS to craft out a loyalty plan for AUR | 2025-08-30
72 | Marcom | Pop Up | Close on strategy and venues | 2025-08-30
4 | Sales | Pop Up | Popup w HS in Berlin | 2025-09-01
109 | Product | Vol 1 | SMS | 2025-09-12
61 | Marcom | Website Production | Integration with CRM | 2025-09-15
70 | Marcom | Loyalty Plan | Coordinate with Fractal to implement the same on the website | 2025-09-15
71 | Marcom | Loyalty Plan | Roll out through Performance, maybe even social | 2025-09-15
73 | Marcom | Pop Up | Identify agency for production | 2025-09-15
110 | Product | Vol 1 | SMS Feedback (with Marketing and Sales) | 2025-09-17
111 | Product | Vol 1 | SMS Order Confirmation by Brand - 300 pairs | 2025-09-17
112 | Product | Vol 1 | Fit Test | 2025-09-17 | WIP
113 | Product | Vol 1 | Mould Opening Confirmation by brand (FVS) | 2025-09-22
114 | Product | Vol 1 | Order Placement - Sales Order Vol 1 | 2025-09-22
1 | Sales | Pop Up | Opening Two Pop-ups (tentatively) one in Dubai - with LEVEL shoes and one in Milan with 10 Corso como | 2025-10-01
2 | Sales | Event | Event Between AUR x HS x 10 Corso como - in presence of AB - a gettogether party | 2025-10-01
74 | Marcom | Pop Up | Finalize pop-up concept, layout & zones, design merchandising & display plans | 2025-10-05
75 | Marcom | Pop Up | Create event invite list (VIPs, friends of brand, partners) | 2025-10-05
115 | Product | Vol 1 | Confirmation Sample | 2025-10-22
3 | Sales | Event | Dinner with AB and influencers in Dubai - Level shoes | 2025-11-01
116 | Product | Vol 1 | Bulk SMS handover by Factory - 400 pairs | 2025-11-02
117 | Product | Vol 1 | Mould Opening Complete | 2025-11-12
118 | Product | Vol 1 | Order Dispatch | 2025-12-23
5 | Sales | Pop Up | Popup with Gallery lafayette in Paris | 2026-01-01
6 | Sales | Event | Selling campaign - B2B show room in Paris + event | 2026-01-01
68 | Marcom | Ms Birla's Role | Assets handover | TBC

## Gant Chart AUR Functions
Sr No | Segment | Sub Segment | Action Pointers | Timeline | Month--> | 2025-12-01 |  |  |  | 2026-01-01 |  |  |  | 2026-02-01 |  |  |  | 2026-03-01 |  |  |  | 2026-04-01 |  |  |  | 2026-05-01 |  |  |  | 2026-06-01 |  |  |  | 2026-07-01 |  |  |  | 2026-08-01 |  |  |  | 2026-09-01
[5 empty] | Current Status | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4
| Trademark | Vol 0 | India TM-AUR & AUR 17 | 2025-01-25 | WIP | bar: 2025-12-01 Wk1
| Trademark | Vol 0 | UAE TM - AUR & AUR 17 | 2025-09-08 | Completed | bar: 2025-12-01 Wk1
| Trademark | Vol 0 | UK TM - AUR & AUR 17 | 2025-09-26 | Completed | bar: 2025-12-01 Wk1
122 | Product | Vol 0 | Final selection of styles/colorways | 2025-12-08 | Completed | bar: 2025-12-01 Wk1
123 | Product | Vol 0 | Mould decision on sizes/ styles | 2025-12-08 | Completed | bar: 2025-12-01 Wk1
124 | Product | Vol 0 | Finalising RRP for Volume 0 | 2025-12-08 | Completed | bar: 2025-12-01 Wk1
138 | Operations | Vol 0 | Finalisation of R&D Agreement | 2025-12-22 | WIP | bar: 2025-12-01 Wk3 to 2025-12-01 Wk4
139 | Operations | Vol 0 | Finalisation of CMA Agreement | 2025-12-22 | WIP | bar: 2025-12-01 Wk3 to 2025-12-01 Wk4
140 | Operations | Vol 0 | Factory Mould Payment | 2025-12-22 | WIP | bar: 2025-12-01 Wk3 to 2025-12-01 Wk4
141 | Operations | Vol 0 | Production Order Payment | 2025-12-22 | WIP | bar: 2025-12-01 Wk3 to 2025-12-01 Wk4
| Product | Caps | Order Confirmation (Styles x Colorways) | 2025-12-22 | Completed | bar: 2025-12-01 Wk3
| Product | Caps | Issuance of PO | 2025-12-22 | WIP | bar: 2025-12-01 Wk3 to 2025-12-01 Wk4
| Product | Vol 0 | Issuance of PO | 2025-12-22 | WIP | bar: 2025-12-01 Wk3 to 2025-12-01 Wk4
| Sales | UK - Strategy | Channel wise Sales Plan | 2025-12-22 | Completed | bar: 2025-12-01 Wk3
| Sales | India - Strategy | Channel wise Sales Plan | 2025-12-22 | Completed | bar: 2025-12-01 Wk3
| Others | Company Name Change | Name change from TACPL to AUR | 2025-12-24 | WIP | bar: 2025-12-01 Wk1 to 2025-12-01 Wk4
| Others | Legal exchanges | Usage of AUR / AUR 17 on packaging / product | 2025-12-27 | WIP | bar: 2025-12-01 Wk3 to 2025-12-01 Wk4
135 | Product | BIS | BIS Factory - India linkage confirmaiton | 2026-01-05 | WIP | bar: 2025-12-01 Wk3 to 2025-12-01 Wk4
125 | Product | Vol 0 | Closure on packaging – Box, Dustbag, butter paper, Hang tags | 2026-01-05 | WIP | bar: 2025-12-01 Wk3 to 2026-01-01 Wk1
127 | Marcom | Development of Brand creative assets | Brand Story Closure | 2026-01-06 | WIP | bar: 2025-12-01 Wk1 to 2026-01-01 Wk1
| Others | Recruitment | Graphic Designer | 2026-01-08 | WIP | bar: 2025-12-01 Wk3 to 2026-01-01 Wk1
| Others | Recruitment | Shopify Developer | 2026-01-08 | WIP | bar: 2025-12-01 Wk3 to 2026-01-01 Wk1
| Others | Recruitment | SCM Consultant | 2026-01-08 | WIP | bar: 2025-12-01 Wk3 to 2026-01-01 Wk1
| Product | Caps | Onboarding of QC Agency | 2026-01-10 | bar: 2026-01-01 Wk1
| Product | Vol 0 | Onboarding of QC Agency | 2026-01-10 | bar: 2026-01-01 Wk2
| Legal | Global | Care instructions & compliance labels (including sustainability (if any)) | 2026-01-10 | bar: 2026-01-01 Wk1
| Legal | Global | Logo usage & brand display legality guidelines | 2026-01-10 | bar: 2026-01-01 Wk1
| Others | Global | Internal & external brand decks | 2026-01-10 | bar: 2026-01-01 Wk1
| Others | Global | Final supply chain flow (Factory → UAE → UK / India) | 2026-01-10 | bar: 2026-01-01 Wk1
| Others | Global | Principal entity confirmation (UAE) | 2026-01-10 | bar: 2026-01-01 Wk1
| Others | Global | Inter-company agreements | 2026-01-10 | bar: 2026-01-01 Wk1
| Others | Global | TP methodology & markup | 2026-01-10 | bar: 2026-01-01 Wk1
65 | Marcom | Launch Event | Event Strategy and format closure | 2026-01-12 | bar: 2026-01-01 Wk1 to 2026-01-01 Wk2
| Product | Vol 0 | CFM Samples w/ Sustainability actions All style All colorway 1 pair | 2026-01-15 | bar: 2025-12-01 Wk4 to 2026-01-01 Wk3
| Operations | India | Warehouse Vendor Onboarding | 2026-01-15 | bar: 2026-01-01 Wk2
| Operations | UK | Warehouse Vendor Onboarding | 2026-01-15 | bar: 2026-01-01 Wk2
| Operations | UK | Mid Mile LSP Onboarding | 2026-01-15 | bar: 2026-01-01 Wk2
| Operations | UK | UK Agent Onboarding | 2026-01-15 | bar: 2026-01-01 Wk2
131 | Operations | Process | Operationalising Zoho with ERP | 2026-01-20 | WIP | bar: 2025-12-01 Wk1 to 2026-01-01 Wk3
| Product | Vol 0 | Brand Feedback | 2026-01-20 | bar: 2026-01-01 Wk3
10 | Marcom | Website Development | Scope, Information and Architecture closure | 2026-01-21 | bar: 2026-01-01 Wk1 to 2026-01-01 Wk3
| Product | Caps | CFM Sample Readiness | 2026-01-21 | bar: 2025-12-01 Wk4 to 2026-01-01 Wk3
52 | Marcom | Development of Brand creative assets | Creative Development & Production Partner Alignment | 2026-01-25 | bar: 2026-01-01 Wk3 to 2026-01-01 Wk4
20 | Marcom | Social Media | Strategy closure | 2026-01-25 | bar: 2026-01-01 Wk3 to 2026-01-01 Wk4
| Product | Vol 0 | Full Size Mould Opening | 2026-02-05 | bar: 2025-12-01 Wk4 to 2026-02-01 Wk2
29 | Marcom | PR | PR strategy and Narrative Closure | 2026-02-07 | bar: 2026-01-01 Wk4 to 2026-02-01 Wk1
8 | Marcom | Development of Brand creative assets | Pre Production | 2026-02-10 | bar: 2026-02-01 Wk2
9 | Marcom | Development of Brand creative assets | Shoot | 2026-02-10 | bar: 2026-02-01 Wk2
53 | Marcom | Website Development | Visual Design and Content Readiness | 2026-02-14 | bar: 2026-01-01 Wk4 to 2026-02-01 Wk2
19 | Marcom | Website Development | Brand Website Launch | 2026-02-14 | bar: 2026-02-01 Wk2
23 | Marcom | Social Media | Calendar Development | 2026-02-14 | bar: 2026-02-01 Wk1 to 2026-02-01 Wk2
67 | Marcom | Launch Event | Production vendor finalisation | 2026-02-14 | bar: 2026-01-01 Wk3 to 2026-02-01 Wk2
46 | Marcom | PR | Asset creation | 2026-02-15 | bar: 2026-02-01 Wk2 to 2026-02-01 Wk3
| Product | Caps | Products Ready EOB ex China | 2026-02-15 | bar: 2025-12-01 Wk4 to 2026-02-01 Wk3
| Product | Caps | Factory QA | 2026-02-20 | bar: 2026-02-01 Wk4
| Product | Vol 0 | All size fit test and quality testing | 2026-02-20 | bar: 2026-02-01 Wk4
25 | Marcom | Social Media | Platform setup | 2026-02-21 | bar: 2026-02-01 Wk2 to 2026-02-01 Wk3
| Product | Caps | Third Party QA | 2026-02-23 | bar: 2026-02-01 Wk4
| Product | Vol 0 | Brand Feedback | 2026-02-25 | bar: 2026-03-01 Wk1
44 | Marcom | Website Development | Backend Development | 2026-02-28 | bar: 2026-02-01 Wk1 to 2026-02-01 Wk4
27 | Marcom | Social Media | Community Response Guidelines | 2026-03-05 | bar: 2026-02-01 Wk4 to 2026-03-01 Wk1
| Product | Caps | -Ship by Sea Freight | 2026-03-09 | bar: 2026-02-01 Wk4 to 2026-03-01 Wk2
12 | Marcom | Website Development | Final Content and Asset Integration | 2026-03-10 | bar: 2026-03-01 Wk2
14 | Marcom | Launch Event | Event Design | 2026-03-10 | bar: 2026-02-01 Wk3 to 2026-03-01 Wk2
| Product | Caps | CHA & Clearance (based on sea freight) | 2026-03-12 | bar: 2026-03-01 Wk2
| Product | Caps | AUR Warehouse or Agent | 2026-03-13 | bar: 2026-03-01 Wk2
45 | Marcom | Website Development | Teaser Website Launched | 2026-03-15 | bar: 2026-03-01 Wk3
63 | Marcom | Website Development | Tracking and Analytics setup | 2026-03-15 | bar: 2026-03-01 Wk2 to 2026-03-01 Wk3
24 | Marcom | Social Media | Content creation and production of teaset launch | 2026-03-15 | bar: 2026-02-01 Wk4 to 2026-03-01 Wk3
15 | Marcom | Launch Event | Asset Creation | 2026-03-15 | bar: 2026-03-01 Wk2 to 2026-03-01 Wk3
64 | Marcom | PR | Pre launch outreach | 2026-03-21 | bar: 2026-04-01 Wk1 to 2026-04-01 Wk3
13 | Marcom | Website Development | Soft Launch/ Testing | 2026-03-25 | bar: 2026-03-01 Wk4
16 | Marcom | Launch Event | Invites | 2026-04-01 | bar: 2026-03-01 Wk3 to 2026-04-01 Wk2
28 | Marcom | Social Media | Social Launch | 2026-04-10 | bar: 2026-03-01 Wk3 to 2026-04-01 Wk2
17 | Marcom | Launch Event | Actual Production | 2026-04-10 | bar: 2026-04-01 Wk2
31 | Marcom | Launch Event | Launch | 2026-04-10 | bar: 2026-04-01 Wk2
7 | Marcom | Development of Brand creative assets | Post Production | 2026-04-21 | bar: 2026-01-01 Wk3 to 2026-04-01 Wk4
54 | Marcom | PR | Launch Outreach and Coverage | 2026-04-25 | bar: 2026-01-01 Wk2; 2026-04-01 Wk3 to 2026-04-01 Wk4
| Product | Vol 0 | Products ready FOB ex Indonesia | 2026-04-25 | bar: 2026-02-01 Wk1 to 2026-04-01 Wk4
| Product | Vol 0 | Factory QA | 2026-04-30 | bar: 2026-04-01 Wk3 to 2026-04-01 Wk4
11 | Marcom | Website Development | Testing | 2026-05-03 | bar: 2026-03-01 Wk1
| Product | Vol 0 | Third Party QA | 2026-05-03 | bar: 2026-04-01 Wk3 to 2026-04-01 Wk4
| Product | Vol 0 | -Ship by Sea Freight | 2026-05-17 | bar: 2026-05-01 Wk1 to 2026-05-01 Wk2
| Product | Vol 0 | CHA & Clearance (based on sea freight) | 2026-05-20 | bar: 2026-05-01 Wk3
| Product | Vol 0 | AUR Warehouse or Agent | 2026-05-21 | bar: 2026-05-01 Wk4
4 | Sales | Pop Up | London Take over Physical Pop Up | 2026-05-31 | bar: 2026-05-01 Wk4
1 | Sales | Pop Up | Pop Up Event | 2026-09-01 | bar: 2026-09-01 Wk1
2
3
5
6